## Sheet1
sprint | task | owner | status | deadline | comment
1 | read the paper | All
1 | get the bed and fasta files from the paper : positives and negatives | Wim | finished |  | cfr Get_BED_FASTA folder
1 | share roadmap excel on github | Wim | finished
1 | prepare some slides for the next presentation on Monday, update the roadmap |  |  | 2018-10-28
1 | do the presentation next Monday |  |  | 2018-10-29
1 | run homer, positives vs negatives and vice versa and send a screenshot to Daphe and Ibrahim |  |  | 2018-10-29
1 | figure out RSAT, run it (positives vs negatives and vice versa) and send a screenshot to Daphe and Ibrahim |  |  | 2018-10-29
1 | find out how you can get the output of RSAT in a format that cluster buster likes (a motif file), and write a script for this
1 | run cbust on RSAT and Homer output
1 | write a parsing script that takes the cluster buster output and produces an feature matrix |  |  |  | Daphne mentioned we should pick up the 'CRM score' as an overall score for a motif<-> enhancer pair
1 | make the actual feature matrix with our data, and maybe also send it to Daphne + Ibrahim |  |  |  | this will be a huge matrix because of the many motives the BORUTA package will boil this down to 10-20 motives
1 | check out MAST package, is there a python alternative, preference ?
1 | check out BORUTA package, is there a python alternative, preference ?
1 | get an idea of the validation and evaluation approach : what is our test set ?(separate out 1 chrom) how do you make a precision recall graph ? ..
1 | read deep learning paper from ibrahim | All
1 | archive/clean up the result from the first dataset on github, so we don't get confused