## Sheet1
sprint | task | owner | status | deadline | comment
1 | read the paper | All
1 | get the bed and fasta files from the paper : positives and negatives | Wim | finished |  | cfr Get_BED_FASTA folder
1 | share roadmap excel on github | Wim | finished
1 | prepare some slides for the next presentation on Monday, update the roadmap |  |  | 2018-10-28
1 | do the presentation next Monday |  |  | 2018-10-29
1 | run homer, positives vs negatives and vice versa and send a screenshot to Daphe and Ibrahim | Wim | finished | 2018-10-29
1 | figure out RSAT, run it (positives vs negatives and vice versa) and send a screenshot to Daphe and Ibrahim |  |  | 2018-10-29
1 | find out how you can get the output of RSAT in a format that cluster buster likes (a motif file), and write a script for this
1 | run cbust on RSAT and Homer output
1 | use I cis target (find motifs, and parse so cbust can run on it)
1 | write a parsing script that takes the cluster buster output and produces a feature matrix | Wim | in progress |  | Daphne mentioned we should pick up the 'CRM score' as an overall score for a motif<-> enhancer pair
1 | make the final feature matrix with all of our data combined, and maybe also send it to Daphne + Ibrahim |  |  |  | this will be a huge matrix because of the many motives the BORUTA package will boil this down to 10-20 motives
1 | check out MAST package, is there a python alternative, preference ?
1 | check out BORUTA package, is there a python alternative, preference ?
1 | get an idea of the validation and evaluation approach : what is our test set ?(separate out 1 chrom) how do you make a precision recall graph ? ..
1 | read deep learning paper from ibrahim | All
1 | archive/clean up the result from the first dataset on github, so we don't get confused
1 | Btw, Ibrahim mentioned that you can also start preparing the sequences for the deep learning models. Basically, you just have to make sure they all have the same length and are accompanied by a label | Wim